## Sheet1
Sprint 1 - Backlog (Team 4)
Sprint 1: Task Description | Duration (Hours) | Member(s) | Status | Mon | Tues | Wed | Thurs | Fri
1. Debug existing application
Become familiar with the code | 2 | All | Completed | 1 | 0 | 0 | 0 | 0
Get application running on physical Android Device/Emulator | 2 | All | Completed | 1 | 0 | 0 | 0 | 0
Connect to Yahoo! Finance API | 1 | Thomas | Completed | 1 | 0 | 0 | 0 | 0
Get all Share Names displaying properly | 1 | Thomas | Completed | 1 | 0 | 0 | 0 | 0
Test code on physical Android Device | 1 | Victor, Adam, Thomas | Completed | 1 | 0 | 0 | 0 | 0
2. Sorting Shares
Create Hashmap to store Share Names and Overall Value | 1 | Thomas, Mark | Completed | 1 | 0 | 0 | 0 | 0
Create TreeMap to sort shares by highest value | 1 | Thomas, Adam | Completed | 1 | 0 | 0 | 0 | 0
Create NavMap to sort values into descending order | 1 | Thomas | Completed | 1 | 0 | 0 | 0 | 0
Increase readability | 2 | Victor, Mark | Completed | 2 | 2 | 0 | 0 | 0
Develop test data | 1 | All | Completed | 1 | 1 | 1 | 0 | 0
Perform test from story card | 2 | Victor, Hamish | Completed | 2 | 2 | 1 | 0 | 0
3. Updates Views
Research graph api's for java android | 2 | Hamish, Adam | Completed | 0 | 0 | 2 | 0 | 0
Research how to collect historic data from yahoo api | 2 | Mark, Victor | Completed | 0 | 0 | 2 | 0 | 0
Plan how to implement this feature | 2 | Thomas, Peter | In Progress | 0 | 0 | 2 | 2 | 1
Code the feature | 4 | Thomas, Peter | To Do | 0 | 0 | 4 | 4 | 4
Test code with sets of data | 2 | Mark, Victor | To Do | 0 | 0 | 2 | 2 | 2
|  |  | Totals: | 15 | 5 | 14 | 8 | 7
NOTE: Started part 3 on Wednesday after consulting with Raleigh. She gave us permission to start another story card since we had finished all that was required for this sprint.
Graphs dips down because we completed task 1 quickly. After completing task 2, Raleigh let us make a start on another story card which resulted in the huge spike on the graph between Tuesday and Wednesday

## Sheet2
Members | Status
Tom | To Do
Mark | In Progress
Victor | Completed
Pete
Adam
Hamish