## Sheet1
Sprint 2 - Backlog (Team 4)
Sprint 2: Task Description | Duration (Hours) | Member(s) | Status | Mon | Tues | Wed | Thurs | Fri | Mon | Tues | Wed | Thurs | Fri
1. Debug existing application
Correct numbers for accurate shares | 1 | Thomas, Victor | Completed | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Make text smaller to fit on screen | 1 | Mark, Hamish | Completed | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Test code on physical Android Device | 1 | Thomas, Victor | Completed | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. Generating Weekly, Montly & Yearly Graph
Research graph api's for java android | 2 | All | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Plan how to collect historic data from yahoo api | 2 | Adam, Peter | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Learn how to use new AndroidPlot library | 2 | All | Completed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Get library set up and running | 1 | Mark, Thomas | Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Create new tab for 'Graphs', and code to run the tab activity | 0.5 | Thomas | Completed | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Create Spinners and populate with appropriate text | 1 | Hamish, Adam | Completed | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Create a graph widget and plot a simple graph | 1 | Victor, Mark | Completed | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Plot lines using the historic data | 1 | Victor, Mark | Completed | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Adjust the aethetics of the graph widget | 6 | Victor, Mark | Completed | 3 | 3 | 3 | 0 | 3 | 3 | 0 | 0 | 0 | 0
Test the spinners are altering the correct time periods | 0.5 | Peter, Adam | Completed | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0
Test the spinners are altering the correct company shares | 0.5 | Peter, Adam | Completed | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0
Test the graph is plotting lines relative to the time period and shares correctly | 0.5 | Peter, Adam | Completed | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0
3. Setting up Alerts
Research UI elements to allow the user to change the alert | 1 | Thomas | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
Insert Sliders | 1 | Thomas | Completed | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
Get Sliders to update with correct value | 1 | Thomas | Completed | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
Get Value from Sliders | 1 | Thomas | Completed | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
Set AlertActivity to update every time a slider is changed. | 1 | Thomas | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
4. Updating Shares as they happen
Correct the summary page so when the tab is clicked it updates the shares | 2 | Thomas | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0
5. JUnit Testing + Refactoring
Identify code to be refactored | 2 | All | Completed | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Refactor Feed Parser file | 3 | Peter, Adam, Hamish | Completed | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Refactor Graph Activity file | 3 | Victor, Mark | Completed | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4
Refactor Rockets file | 1 | Thomas | Completed | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 4 | 4
Refactor Alerts file | 1 | Thomas | Completed | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Junit Testing: StockManagerTest | 8 | All | Completed | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 0
Junit Testing: FinanceTest | 8 | All | Completed | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 0 | 0
Junit Testing: FeedParserTest | 8 | All | Completed | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 0 | 0
|  |  | Totals: | 28 | 25 | 20.5 | 16.5 | 18.5 | 23.5 | 19 | 17 | 15 | 14
Sprint 2: Estimated Velocity = 3
This is based on the agreed upon user stories for sprint 2.
Sprint 2: Final Value = 12
This is based on the user stories that were completed in sprint 2.
Sprint 1: Velocity = 5
[5 empty] | Name | Value
[5 empty] | Sprint 1 | 5
[5 empty] | Sprint 2 | 12

## Sheet2
Members | Status
Tom | To Do
Mark | In Progress
Victor | Completed
Pete
Adam
Hamish